## Slide 1
A
3
B
5
Start
0
C
3
D
1
E
8
F
3
G
3
H
1
I
2
Finish
0
Early Finish Time = Early Start Time + duration
0
3
3
4
0
5
5
8
8
E depends on C and D. C and D’s Early Finish Time are 8 and 4 respectively. We choose the larger one.
16
16
19
8
11
H depends on E and G. E and G’s Early Finish Time are 16 and 11 respectively. We choose the larger one.
16
17
17
19
19
19
Late Start Time = Late Finish Time - duration
19
19
19
17
17
16
16
13
19
16
Late Finish Time of E depends on F and H’s Late Start Time, both of them are 16.
16
8
8
7
8
5
5
0
7
4
Late Finish Time of A and B are 4 and 0 respectively. We choose the smaller one.
0
0
Free Float (Slack Time) = Late Finish Time - Early Finish Time
0
4
0
0
4
0
0
5
0
0
0
0
0
Lecture Demo
Late Finish Time of C depends on G and E’s Late Start Time, we choose the smallest one.
Total Slack Time of each path = 19-(Total duration of Activities in the path):
A-D-E-F = 4 | A-D-E-H-I = 4 | B-C-E-F = 0 | B-C-E-H-I = 0 | B-C-G-H-I = 5
Total Slack Time = 0 is(are) the critical path(s): B-C-E-F and B-C-E-H-I